## Issue Tracker
Ascendons CRM — Issue & Feature Tracker
Generated: 2026-04-18 ¦ Total Issues: 50 ¦ P0: 2 ¦ P1: 15 ¦ P2: 25 ¦ P3: 8
ID | Type | Category | Title | Description | Affected Files | Priority | Status | Est. Effort | Sprint | Assignee | Reporter | Labels | Notes
CRM-001 | Bug | Security | CRITICAL: MongoDB credentials exposed in source code | Production DB credentials hardcoded in application.properties (mongodb+srv://dev_divisha_app:Divisha%40123@...). Must be moved to environment variables immediately. | backend/src/main/resources/application.properties | P0 - Critical | Open | 1h | Immediate
CRM-002 | Bug | Security | Missing @PreAuthorize on ~144 endpoints | Out of 423 HTTP endpoints only ~279 have @PreAuthorize. Unprotected endpoints allow unauthenticated or unauthorized access. | Multiple controllers | P1 - High | Open | 3d | Sprint 1
CRM-003 | Bug | Security | Missing @Valid on ~76 POST/PUT endpoints | 166 POST/PUT/PATCH endpoints exist but only ~90 have @Valid. Allows invalid data through without bean validation. | Multiple controllers | P1 - High | Open | 2d | Sprint 1
CRM-004 | Bug | Backend | System.out.println debug statements in production | Two System.out.println calls in AuditLogController (line 1) and ProposalService (line 533) must be replaced with proper SLF4J logging. | AuditLogController.java, ProposalService.java | P1 - High | Open | 30m | Sprint 1
CRM-005 | Bug | Frontend | 230+ console.log statements in production frontend | Extensive console.log/error/warn across 114+ frontend files. Leaks debug information and impacts performance. | frontend/app/ (all pages) | P2 - Medium | Open | 2d | Sprint 2
CRM-006 | Feature | Backend | Email notification service not implemented | EmailNotificationService only logs emails - does not send via SendGrid/SES/SMTP. Invitations and password resets fail silently. | EmailNotificationService.java | P1 - High | Open | 3d | Sprint 1
CRM-007 | Feature | Backend | Proposal email notifications missing | ProposalService TODOs at line 515 (send email on proposal sent) and 591-592 (auto-create Opportunity / update Opportunity stage on accept). | ProposalService.java | P1 - High | Open | 1d | Sprint 1
CRM-008 | Feature | Backend | Async data export not implemented | DataExportController.requestDataExport() has TODO for async export with job queue. Large exports block HTTP threads. | DataExportController.java | P2 - Medium | Open | 3d | Sprint 2
CRM-009 | Feature | Backend | Webhook async delivery not triggered | WebhookEventService line 231 TODO: Trigger async webhook delivery. Webhook events are created but never dispatched. | WebhookEventService.java | P2 - Medium | Open | 2d | Sprint 2
CRM-010 | Feature | Backend | Lead behavioral scoring returns hardcoded 0 | LeadScoringService.calculateBehavioralScore() returns 0. Should track email opens/website visits/form submissions. | LeadScoringService.java | P2 - Medium | Open | 2d | Sprint 2
CRM-011 | Feature | Backend | Lead scoring industry weights hardcoded | LeadScoringService line 93 TODO: Make target industries configurable. Currently hardcoded to Technology/Finance/Healthcare. | LeadScoringService.java | P3 - Low | Open | 1d | Sprint 3
CRM-012 | Feature | Backend | Warranty expiry alerts not sent to users | AssetWarrantyExpiryScheduler logs 30/60/90-day alerts but does not call NotificationService. TODO comment at line 43. | AssetWarrantyExpiryScheduler.java | P2 - Medium | Open | 1d | Sprint 2
CRM-013 | Feature | Backend | Audit logging missing for user operations | UserService TODOs at lines 182/450/474: user create/update/disable not being written to audit log. | UserService.java | P2 - Medium | Open | 1d | Sprint 2
CRM-014 | Feature | Backend | Organization invitation limits not enforced | OrganizationInvitationService TODOs at lines 60/72/162/245: usage limit validation and UserRepository methods not implemented. | OrganizationInvitationService.java | P2 - Medium | Open | 2d | Sprint 2
CRM-015 | Feature | Backend | Last login IP address not recorded | AuthService line 206 TODO: Set lastLoginIP from HTTP request context. Security audit trail incomplete. | AuthService.java | P3 - Low | Open | 2h | Sprint 3
CRM-016 | Feature | Backend | Tenant analytics growth calculation stub | TenantAnalyticsService line 60 TODO: Implement actual growth calculation. Returns placeholder values. | TenantAnalyticsService.java | P3 - Low | Open | 1d | Sprint 3
CRM-017 | Feature | Backend | GPS spoofing detection not implemented | AttendanceService hardcodes isGpsSpoofingDetected=false. GpsSpoofingDetector exists but not wired into field check-in flow. | AttendanceService.java | P2 - Medium | Open | 2d | Sprint 2
CRM-018 | Feature | Backend | 3-way invoice matching not implemented | PurchaseOrder entity has invoiceMatchStatus/grnId/vendorInvoiceAmount fields but no service logic compares PO qty×price vs GRN vs vendor invoice. | PurchaseOrderApprovalService.java | P2 - Medium | Open | 3d | Sprint 2
CRM-019 | Feature | Backend | Contract billing cycle auto-invoicing not implemented | Plan specifies auto-generate invoice on billing cycle due date using ProposalService. ContractBillingCycle entity exists but no scheduler. | ContractService.java | P2 - Medium | Open | 2d | Sprint 2
CRM-020 | Feature | Backend | Customer sign-off OTP flow not implemented | WorkOrder has customerSignOff field and SignOffMethod enum but no OTP send/verify endpoints exist. | WorkOrderController.java | P2 - Medium | Open | 2d | Sprint 2
CRM-021 | Feature | Backend | WorkOrder photo upload endpoint missing | Plan specifies multipart photo upload endpoint for work orders. WorkOrderPhoto entity exists but no controller endpoint. | WorkOrderController.java | P2 - Medium | Open | 1d | Sprint 2
CRM-022 | Feature | Backend | Work order auto-assignment service missing | Plan specifies WorkOrderAutoAssignService matching engineer by skill+location+workload. Not implemented. | Missing file | P2 - Medium | Open | 3d | Sprint 3
CRM-023 | Feature | Backend | Dealer territory → lead assignment not linked | Plan specifies extending LeadAssignmentConfig with territory→dealerId mapping. Not implemented. | DealerService.java | P3 - Low | Open | 2d | Sprint 3
CRM-024 | Feature | Frontend | PO approval workflow UI missing | PurchaseOrderApprovalController exists with submit/approve/reject/pending-approval endpoints but no frontend pages. | frontend/app/procurement/purchase-orders/ | P1 - High | Open | 2d | Sprint 1
CRM-025 | Feature | Frontend | Dispatch map view missing | /dispatch/map page for Leaflet/Google Maps view of engineer locations + open WOs not implemented. EngineerLocationController exists. | frontend/app/dispatch/map/ | P1 - High | Open | 3d | Sprint 1
CRM-026 | Feature | Frontend | Engineer management admin page missing | /admin/engineers page for engineer capacity/availability/skill tags not implemented. | frontend/app/admin/engineers/ | P1 - High | Open | 2d | Sprint 1
CRM-027 | Feature | Frontend | Dealer tier configuration UI missing | /admin/dealer-tiers page for tier benefit configuration not implemented. | frontend/app/admin/dealer-tiers/ | P3 - Low | Open | 1d | Sprint 3
CRM-028 | Feature | Frontend | Checklist template management UI missing | /admin/settings/checklists pages for creating/editing checklist templates not verified as implemented. | frontend/app/admin/settings/checklists/ | P2 - Medium | Open | 2d | Sprint 2
CRM-029 | Feature | Frontend | Asset categories admin page missing | /admin/settings/asset-categories page for managing categories with required skills not verified. | frontend/app/admin/settings/asset-categories/ | P2 - Medium | Open | 1d | Sprint 2
CRM-030 | Feature | Frontend | Service analytics dashboard - engineer productivity names | Engineer productivity table shows engineerId not names. Need to resolve userId → name via user API. | frontend/app/analytics/service/page.tsx | P2 - Medium | Open | 4h | Sprint 2
CRM-031 | Feature | Frontend | Inventory analytics top-consumed shows productId not names | Top consumed parts list shows productId. Should resolve to product name via product API. | frontend/app/analytics/inventory/page.tsx | P2 - Medium | Open | 4h | Sprint 2
CRM-032 | TechDebt | Frontend | TypeScript 'any' type used 130+ times across frontend | Widespread any type usage reduces type safety. Proper interfaces should be defined for all API responses. | frontend/lib/*.ts and frontend/app/**/*.tsx | P3 - Low | Open | 5d | Sprint 3
CRM-033 | TechDebt | Frontend | Missing error boundary components on individual pages | Only global error.tsx exists. Individual pages need error states for fetch failures/network errors/permission denied. | frontend/app/ (all pages) | P2 - Medium | Open | 2d | Sprint 2
CRM-034 | TechDebt | Frontend | Environment variables not documented | NEXT_PUBLIC_API_URL and backend env vars not documented in .env.example or README. | Root directory | P2 - Medium | Open | 2h | Sprint 1
CRM-035 | TechDebt | Backend | Null returns instead of Optional/exceptions in services | Multiple services return null on failure (AttendanceService mapper, ProfileService, UserService). Should use Optional<T> or throw ResourceNotFoundException. | Multiple service files | P2 - Medium | Open | 2d | Sprint 2
CRM-036 | TechDebt | Backend | OrganizationInvitationService UserRepository methods missing | Service calls commented-out repository methods (existsByEmailAndTenantId etc) that are not defined in UserRepository interface. | OrganizationInvitationService.java | P2 - Medium | Open | 4h | Sprint 1
CRM-037 | TechDebt | Backend | CORS allows raw IP without verification | application.properties CORS allows http://52.20.26.167 — verify this is a legitimate production IP and document it. | application.properties | P2 - Medium | Open | 2h | Sprint 1
CRM-038 | TechDebt | Backend | Proposal state machine not formally documented | ProposalService accepts proposals in SENT/PENDING_APPROVAL/PENDING_ON_CUSTOMER but state transitions not modeled as explicit state machine. | ProposalService.java | P3 - Low | Open | 1d | Sprint 3
CRM-039 | TechDebt | Backend | PO auto-reorder number uniqueness not guaranteed | PartsConsumptionService creates draft PO with 'PO-AUTO-{timestamp}'. No sequence-based number like other entities. May collide under concurrent requests. | PartsConsumptionService.java | P2 - Medium | Open | 2h | Sprint 2
CRM-040 | TechDebt | Frontend | Hardcoded localhost fallback in WebSocket and Chat providers | ChatPanel.tsx and WebSocketProvider.tsx hardcode ws://localhost:8080 as fallback. Must use env var only in production builds. | ChatPanel.tsx, WebSocketProvider.tsx | P2 - Medium | Open | 2h | Sprint 1
CRM-041 | Feature | Frontend | Purchase orders list page missing | No /procurement/purchase-orders list page exists. POs can be created through GRN flow but not browsed/managed directly. | frontend/app/procurement/purchase-orders/ | P1 - High | Open | 2d | Sprint 1
CRM-042 | Feature | Backend | PO number generation service missing | PurchaseOrderApprovalService generates auto-PO numbers ad hoc (PO-AUTO-timestamp). Needs proper PurchaseOrderIdGeneratorService like other modules. | Missing file | P2 - Medium | Open | 2h | Sprint 2
CRM-043 | Bug | Frontend | Sidebar navigation section 'Service Analytics' item has no module guard | Analytics/service and Analytics/inventory nav items in Sidebar may show for users without SERVICE_ANALYTICS permission depending on how module check is done. | Sidebar.tsx | P2 - Medium | Open | 2h | Sprint 1
CRM-044 | Feature | Backend | Real-time engineer location WebSocket broadcast on geo update | GeoTrackingService saves location and should broadcast via SimpMessagingTemplate to /topic/geo/{tenantId} for live map — verify broadcast is implemented. | GeoTrackingService.java | P2 - Medium | Open | 4h | Sprint 2
CRM-045 | Feature | Frontend | Parts request creation from work order detail missing | WO detail page /work-orders/[id]/parts should allow engineer to raise new parts request inline. Verify form exists. | frontend/app/work-orders/[id]/parts/page.tsx | P1 - High | Open | 1d | Sprint 1
CRM-046 | TechDebt | Backend | EscalationService uses findAll() on all tenants | EscalationService.evaluateAllRules() calls ruleRepository.findAll() loading all tenant rules at once. Should be paginated or indexed query. | EscalationService.java | P2 - Medium | Open | 4h | Sprint 2
CRM-047 | TechDebt | Backend | AssetWarrantyExpiryScheduler uses findAll() for warranty check | Scheduler calls assetRepository.findAll() and filters in memory. Should use findByTenantIdAndWarrantyExpiryBeforeAndIsDeletedFalse() for each tenant. | AssetWarrantyExpiryScheduler.java | P2 - Medium | Open | 2h | Sprint 2
CRM-048 | Feature | Backend | ContractVisitScheduler has no tenant isolation | ContractVisitScheduler queries visitRepository.findAll() without tenant filter. All tenants processed in shared context which breaks multi-tenancy. | ContractVisitScheduler.java | P0 - Critical | Open | 4h | Immediate
CRM-049 | Bug | Backend | DealerPerformanceService scheduler calls dealerOrderRepository.findAll() | Monthly aggregation calls findAll() loading ALL orders across ALL tenants into memory. Must filter by tenant. | DealerPerformanceService.java | P1 - High | Open | 4h | Sprint 1
CRM-050 | Feature | Frontend | Vendor detail page missing linked RFQ history | Vendor detail /vendors/[id] should show related RFQs and POs but only shows rate contracts. | frontend/app/vendors/[id]/page.tsx | P3 - Low | Open | 4h | Sprint 3

## Summary
Issue Tracker Summary
Priority Breakdown
Priority | Count
P0 - Critical | 2
P1 - High | 15
P2 - Medium | 25
P3 - Low | 8
Total | 50
By Type
Type | Count
Bug | 8
Feature | 29
TechDebt | 13
By Category
Category | Count
Security | 4
Backend | 18
Frontend | 16
TechDebt | 12
By Sprint
Sprint | Count
Immediate | 3
Sprint 1 | 15
Sprint 2 | 22
Sprint 3 | 10

## Test Scenarios
Ascendons CRM — Test Scenarios & QA Checklist
Total Scenarios: 120 ¦ Modules: 18 ¦ Types: Functional · Integration · Security · Edge Case · Regression · Performance
TC-ID | Module | Feature / Scenario | Test Steps | Expected Result | Type | Priority | Status | Related Issue | Notes
AUTH & MULTI-TENANCY
TC-001 | Auth | User Login - Valid Credentials | 1. POST /api/v1/auth/login with valid email+password 2. Inspect response | 200 OK with JWT token; token contains tenantId, userId, roles | Functional | Critical | Untested
TC-002 | Auth | User Login - Invalid Password | 1. POST /api/v1/auth/login with wrong password | 401 Unauthorized; no token returned; error message shown | Functional | High | Untested
TC-003 | Auth | JWT Expiry Handling | 1. Use an expired JWT token in Authorization header 2. Call any protected endpoint | 401 Unauthorized; frontend redirects to /login | Functional | High | Untested
TC-004 | Auth | Multi-Tenant Data Isolation | 1. Log in as Tenant A user 2. Call GET /leads 3. Log in as Tenant B user 4. Call GET /leads | Each tenant sees ONLY their own data; no cross-tenant leakage | Security | Critical | Untested | CRM-048 | Most critical test
TC-005 | Auth | Role-Based Access - Forbidden Action | 1. Log in as Field Engineer role 2. Attempt DELETE /leads/{id} | 403 Forbidden; action blocked by RBAC | Security | Critical | Untested | CRM-002
TC-006 | Auth | Password Reset Flow | 1. POST /auth/forgot-password with email 2. Check email for reset link 3. POST /auth/reset-password with token | Reset email sent; password updated; old token invalidated | Functional | High | Untested | CRM-006 | Email service must be real
TC-007 | Auth | Tenant Registration | 1. POST /auth/register with org name, email, password 2. Verify tenant created in DB | 201 Created; tenant record; default roles seeded; welcome email sent | Functional | High | Untested
LEAD MANAGEMENT
TC-008 | Leads | Create Lead - All Required Fields | 1. Navigate to /leads/new 2. Fill all required fields 3. Submit form | Lead created with auto-generated ID (LEAD-YYYY-MM-XXXXX); appears in list | Functional | High | Untested
TC-009 | Leads | Create Lead - Missing Required Field | 1. Submit lead form without firstName | Form shows validation error; no API call made; lead not created | Functional | High | Untested | CRM-003
TC-010 | Leads | Lead BANT Score Calculation | 1. Create a lead with Budget=High, Authority=Decision Maker, Need=Strong, Timeline=Immediate 2. Check score | BANT score ≥ 80; lead classified as Hot | Functional | Medium | Untested
TC-011 | Leads | Lead Status Transition | 1. Open lead in NEW status 2. Change status to CONTACTED 3. Change to QUALIFIED | Status updates saved; history log records each transition with timestamp | Functional | High | Untested
TC-012 | Leads | Lead Assignment to User | 1. Open a lead 2. Assign to a team member 3. Team member logs in | Assignee sees lead in their queue; notification sent to assignee | Functional | Medium | Untested
TC-013 | Leads | Lead Conversion to Opportunity | 1. Open a QUALIFIED lead 2. Click Convert 3. Fill opportunity details | Opportunity created; lead status set to CONVERTED; linked records visible | Functional | High | Untested
TC-014 | Leads | Bulk Lead Delete | 1. Select 3 leads via checkbox 2. Click Bulk Delete 3. Confirm dialog | All 3 leads soft-deleted; removed from list; recoverable from DB | Functional | Medium | Untested
TC-015 | Leads | Lead Search & Filter | 1. Search by company name 2. Filter by status=NEW 3. Sort by createdAt DESC | Only matching leads shown; pagination works correctly | Functional | Medium | Untested
SALES PIPELINE & OPPORTUNITIES
TC-016 | Opportunities | Create Opportunity | 1. Navigate to /opportunities/new 2. Fill deal name, value, stage, close date 3. Submit | Opportunity created; visible in pipeline kanban and list view | Functional | High | Untested
TC-017 | Opportunities | Move Opportunity Across Pipeline Stages | 1. Open opportunity 2. Change stage from Prospecting → Qualification → Proposal | Stage transitions saved; probability auto-updates per stage; history logged | Functional | High | Untested
TC-018 | Opportunities | Opportunity Win/Loss | 1. Set opportunity to Closed Won 2. Set another to Closed Lost with reason | Won: revenue recorded. Lost: reason saved. Both removed from active pipeline. | Functional | Medium | Untested
ASSETS & EQUIPMENT
TC-019 | Assets | Create Asset | 1. Navigate to /assets/new 2. Fill serial no, model, brand, category, account 3. Submit | Asset created with auto code (ASSET-YYYY-MM-XXXXX); visible in /assets | Functional | High | Untested
TC-020 | Assets | Duplicate Serial Number Rejection | 1. Create asset with serialNo=SN001 2. Try creating another with same serialNo | 409 Conflict returned; second asset not created; error shown in UI | Functional | High | Untested
TC-021 | Assets | Asset Warranty Expiry Alert | 1. Create asset with warrantyExpiry = today + 25 days 2. Run AssetWarrantyExpiryScheduler manually | Log entry shows 30-day warning for the asset; notification sent (once wired) | Functional | Medium | Untested | CRM-012
TC-022 | Assets | Filter Assets by Account | 1. Navigate to /assets?accountId=ACC-001 | Only assets linked to that account returned; others excluded | Functional | Medium | Untested
TC-023 | Assets | Asset Status Update | 1. Open asset detail 2. Change status from ACTIVE to UNDER_REPAIR | Status updated; reflected in list view with correct badge color | Functional | Low | Untested
AMC / CONTRACT MANAGEMENT
TC-024 | Contracts | Create AMC Contract | 1. Navigate to /contracts/new 2. Select type=AMC, account, assets, SLA config 3. Submit | Contract created with number CON-XXXXX; visits auto-generated per visitFrequency | Functional | High | Untested
TC-025 | Contracts | Activate Contract | 1. Open DRAFT contract 2. Click Activate | Status changes to ACTIVE; start date recorded; SLA clock begins | Functional | High | Untested
TC-026 | Contracts | Contract Visit Auto-WO Creation | 1. Create contract with visit scheduled for today 2. Trigger ContractVisitScheduler | Work order of type AMC_VISIT auto-created; linked to visit record | Integration | High | Untested | CRM-048 | Check tenant isolation
TC-027 | Contracts | Contract Renewal | 1. Open EXPIRED contract 2. Click Renew with new dates | New contract created; old one marked RENEWED; visits regenerated | Functional | Medium | Untested
TC-028 | Contracts | Contract SLA Config Feed to Work Order | 1. Contract has SLA responseHrs=4, resolutionHrs=8 2. Create WO from this contract | WO.slaDeadline = createdAt + 8h; SLA breach triggers if exceeded | Integration | High | Untested
WORK ORDER MANAGEMENT
TC-029 | Work Orders | Create Work Order | 1. Navigate to /work-orders/new 2. Fill type, priority, asset, account 3. Submit | WO created with number WO-XXXXX; status=OPEN; SLA deadline calculated | Functional | Critical | Untested
TC-030 | Work Orders | Work Order State Machine - Full Flow | 1. Create WO (OPEN) 2. Assign engineer (ASSIGNED) 3. Engineer marks En Route 4. Arrive on site (ON_SITE) 5. Start checklist (IN_PROGRESS) 6. Complete checklist (COMPLETED) | Each status transition succeeds; invalid transitions (e.g. OPEN→COMPLETED) rejected with 400 | Functional | Critical | Untested
TC-031 | Work Orders | SLA Breach Detection | 1. Create WO with slaDeadline = now - 1 hour 2. Run SlaBreachScheduler | WO.slaBreached=true; escalation rule fires if configured | Functional | High | Untested
TC-032 | Work Orders | Assign Engineers to WO | 1. Open WO in OPEN status 2. Assign 2 engineers | Status changes to ASSIGNED; both engineers see WO in their queue | Functional | High | Untested
TC-033 | Work Orders | Reopen Completed Work Order | 1. WO in COMPLETED status 2. Click Reopen | Status = REOPENED; reopenCount incremented; new SLA deadline set | Functional | Medium | Untested
TC-034 | Work Orders | Parts Deduction on WO Closure | 1. Add part (qty=2) to WO.partsUsed 2. Close WO | Product.stockQuantity reduced by 2; StockTransaction created with type=PRODUCTION_OUT | Integration | High | Untested
TC-035 | Work Orders | Insufficient Stock on WO Closure | 1. Add part with qty > available stock to WO 2. Attempt to close WO | 400 Bad Request: 'Insufficient stock'; WO stays in IN_PROGRESS; stock unchanged | Edge Case | High | Untested
TC-036 | Work Orders | Checklist Mandatory Item Fail Blocks Completion | 1. Start checklist with mandatory item 2. Mark item as FAIL with failureAction=Block 3. Try to complete checklist | Completion blocked; error message shown; WO cannot advance to COMPLETED | Functional | High | Untested
TC-037 | Work Orders | Kanban View Displays Correct Columns | 1. Navigate to /work-orders 2. Switch to Kanban view | WOs grouped by status; drag is not required but cards show correct status column | Functional | Medium | Untested
SERVICE REQUESTS
TC-038 | Service Requests | Create Service Request | 1. Navigate to /service-requests/new 2. Fill description, source, priority, account 3. Submit | SR created with number SR-XXXXX; status=OPEN; SLA clock starts | Functional | High | Untested
TC-039 | Service Requests | Acknowledge Service Request | 1. Open SR in OPEN status 2. Click Acknowledge | Status = ACKNOWLEDGED; acknowledgedAt timestamp saved | Functional | High | Untested
TC-040 | Service Requests | Convert SR to Work Order | 1. Open ACKNOWLEDGED SR 2. Click Convert to WO 3. Fill WO details | WO created and linked to SR; SR status = WO_CREATED; workOrderId populated | Integration | High | Untested
TC-041 | Service Requests | SR Unacknowledged Escalation | 1. Create SR with conditionMinutes=30 escalation rule 2. Wait / manually trigger evaluator after 30 min | EscalationLog created for SR; L1 users notified | Integration | Medium | Untested | CRM-046
DISPATCH & SCHEDULING
TC-042 | Dispatch | View Engineer Schedule for Date | 1. Navigate to /dispatch 2. Select today's date | Engineer schedule tiles appear; availability badges shown (AVAILABLE/ON_JOB/LEAVE) | Functional | High | Untested
TC-043 | Dispatch | Dispatch Work Order to Engineer | 1. Open dispatch board 2. Click Dispatch on open WO 3. Select AVAILABLE engineer 4. Confirm | WO status → ASSIGNED; DispatchAssignment created; EngineerSchedule updated to ON_JOB | Functional | High | Untested
TC-044 | Dispatch | Cannot Dispatch to ON_JOB Engineer | 1. Try to dispatch WO to engineer with availability=ON_JOB | Warning shown; dispatch either blocked or flagged as overload | Edge Case | Medium | Untested
TC-045 | Dispatch | Reassign Work Order | 1. WO assigned to Engineer A 2. Reassign to Engineer B with reason | Old engineer's schedule slot removed; new engineer assigned; audit log entry created | Functional | Medium | Untested
GEO-TRACKING
TC-046 | Geo-Tracking | Engineer Location Update | 1. POST /geo/location with lat, lng, workOrderId 2. GET /geo/locations | Location saved; TTL set for 24h; latest location returned in GET | Functional | High | Untested
TC-047 | Geo-Tracking | Geo-Event: Arrived Triggers WO ON_SITE | 1. POST /geo/events with eventType=Arrived, workOrderId of EN_ROUTE WO | WO status auto-transitions to ON_SITE; WorkOrderGeoEvent persisted | Integration | High | Untested
TC-048 | Geo-Tracking | Location TTL Expiry | 1. Insert engineer location 2. Wait 24h (or set TTL to 1s in test) 3. Query location | Record automatically deleted by MongoDB TTL index | Functional | Low | Untested
SKILL MATRIX
TC-049 | Skill Matrix | Add Skill to Technician | 1. Navigate to /skill-matrix 2. Enter userId 3. Add Skill: VRF, EXPERT, with cert details | Skill record created; appears in skills table; proficiency badge shows EXPERT | Functional | Medium | Untested
TC-050 | Skill Matrix | Add Training Record | 1. Add training: OEM training, score=90, passed=true | Training record saved; pass badge (green tick) shown in table | Functional | Medium | Untested
TC-051 | Skill Matrix | Expiring Certification Alert | 1. Add skill with expiryDate = today + 25 days 2. Call GET /skill-matrix/expiring?days=30 | Skill returned in expiring list; alert should be triggered | Functional | Medium | Untested
SPARE PARTS & PARTS REQUESTS
TC-052 | Parts Requests | Create Parts Request from WO | 1. Open WO in IN_PROGRESS status 2. Navigate to /work-orders/{id}/parts 3. Add parts request | PartsRequest created; status=PENDING; WO status may change to PENDING_SPARES | Functional | High | Untested | CRM-045
TC-053 | Parts Requests | Approve Parts Request | 1. Open PENDING parts request in /parts-requests 2. Click Approve | Status = APPROVED; stock reserved; WebSocket push to engineer | Functional | High | Untested
TC-054 | Parts Requests | Reject Parts Request with Reason | 1. Open PENDING parts request 2. Click Reject 3. Enter reason | Status = REJECTED; reason saved; engineer notified | Functional | Medium | Untested
TC-055 | Parts Requests | Dispatch Parts | 1. APPROVED parts request 2. Click Dispatch | Status = DISPATCHED; dispatchedAt timestamp saved | Functional | Medium | Untested
TC-056 | Parts Requests | Receive Parts | 1. DISPATCHED parts request 2. Click Mark Received | Status = RECEIVED; receivedAt saved; WO can resume IN_PROGRESS | Functional | Medium | Untested
TC-057 | Parts | Auto-Reorder PO Created on Low Stock | 1. Set product reorderPoint=10, stockQty=12 2. Close WO consuming 5 units (stockQty → 7) 3. Check purchase_orders collection | Draft PO auto-created for the product; poNumber starts with PO-AUTO- | Integration | High | Untested | CRM-039 | Verify no duplicates
VENDOR MANAGEMENT
TC-058 | Vendors | Create Vendor | 1. Navigate to /vendors/new 2. Fill companyName, contactPerson, email, GSTIN 3. Submit | Vendor created; vendorCode auto-generated (VEN-XXXXX); default rating=3 | Functional | High | Untested
TC-059 | Vendors | Update Vendor Rating | 1. Open vendor detail 2. Click 4-star rating 3. Confirm update | POST /vendors/{id}/rating with rating=4; vendor.rating updated; badge reflects change | Functional | Medium | Untested
TC-060 | Vendors | Blacklist Vendor | 1. Change vendor status to BLACKLISTED | Vendor marked BLACKLISTED; badge shows red; should be excluded from RFQ auto-suggestions | Functional | Medium | Untested
TC-061 | Vendors | Vendor Detail Shows Rate Contracts | 1. Create rate contract for vendor 2. Open vendor detail page | Rate contracts section on vendor detail page shows associated contracts | Functional | Low | Untested | CRM-050
PROCUREMENT (RFQ / GRN / RATE CONTRACTS / PO)
TC-062 | RFQ | Create RFQ | 1. Navigate to /procurement/rfq 2. Click Create 3. Add items, select vendors, set deadline | RFQ created with status=OPEN; RFQ number auto-generated | Functional | High | Untested
TC-063 | RFQ | Submit Vendor Response | 1. Open RFQ 2. POST /procurement/rfq/{id}/vendor-response with vendorId, unitPrice, deliveryDays | Vendor response saved under RFQ; visible in comparison table on RFQ detail page | Functional | High | Untested
TC-064 | RFQ | Select Vendor Closes RFQ | 1. Open RFQ with at least one vendor response 2. Click Select Vendor | RFQ status = CLOSED; selectedVendorId populated; other vendors notified (future) | Functional | High | Untested
TC-065 | GRN | Create GRN Against PO | 1. Navigate to /procurement/grn 2. Create GRN: poId, receivedDate, lineItems, qualityStatus | GRN created with number GRN-XXXXX; linked to PO; PO status may update to RECEIVING | Functional | High | Untested
TC-066 | GRN | GRN Quality Status: Partially Accepted | 1. Create GRN with receivedQty < orderedQty for one item 2. Set qualityStatus=PARTIALLY_ACCEPTED | GRN saved; PO remains in RECEIVING state; remaining qty tracked | Edge Case | Medium | Untested
TC-067 | Rate Contracts | Create Rate Contract | 1. Navigate to /procurement/rate-contracts 2. Create with vendorId, items, validFrom, validTo | Rate contract created with RC number; status=ACTIVE; appears in active contracts list | Functional | High | Untested
TC-068 | Rate Contracts | Terminate Rate Contract | 1. Open active rate contract 2. Click Terminate | Status = TERMINATED; no longer appears in active list | Functional | Medium | Untested
TC-069 | PO Approval | Submit PO for Approval - Amount < 50k | 1. Create PO with totalAmount=30000 2. Click Submit for Approval | approvalWorkflow has 1 step (L1 only); status = SUBMITTED | Functional | High | Untested | CRM-024
TC-070 | PO Approval | Submit PO for Approval - Amount 50k-5L | 1. Create PO with totalAmount=200000 2. Submit for Approval | approvalWorkflow has 2 steps (L1 + L2); status = SUBMITTED | Functional | High | Untested | CRM-024
TC-071 | PO Approval | Submit PO for Approval - Amount > 5L | 1. Create PO with totalAmount=600000 2. Submit for Approval | approvalWorkflow has 3 steps (L1 + L2 + L3); status = SUBMITTED | Functional | High | Untested | CRM-024
TC-072 | PO Approval | L1 Approve → L2 Required Next | 1. SUBMITTED PO (L1+L2 workflow) 2. L1 approver calls POST /approve?level=L1 | L1 step status = Approved; PO still SUBMITTED; L2 pending | Functional | High | Untested | CRM-024
TC-073 | PO Approval | Skip L1 and Approve at L2 - Should Fail | 1. SUBMITTED PO (L1+L2 workflow) 2. Try to approve at L2 without L1 approval | 400 Bad Request: Level L1 approval required first | Edge Case | High | Untested | CRM-024
TC-074 | PO Approval | Reject PO at Any Level | 1. SUBMITTED PO 2. POST /reject?level=L1 with reason | PO status = CANCELLED; rejectionReason saved; step status = Rejected | Functional | Medium | Untested | CRM-024
DEALER MANAGEMENT
TC-075 | Dealers | Create Dealer | 1. Navigate to /dealers/new 2. Fill companyName, tier=GOLD, creditLimit=500000 3. Submit | Dealer created with dealerCode DLR-XXXXX; status=ACTIVE; credit utilization=0% | Functional | High | Untested
TC-076 | Dealers | Place Dealer Order Within Credit Limit | 1. Dealer has creditLimit=100000, currentCreditUsed=0 2. Place order totalValue=50000 | Order created; currentCreditUsed → 50000; credit utilization shows 50% | Functional | High | Untested
TC-077 | Dealers | Place Order Exceeding Credit Limit | 1. Dealer creditLimit=100000, currentCreditUsed=80000 2. Try placing order totalValue=30000 | 400 Bad Request: credit limit exceeded; order not created; UI shows error | Edge Case | Critical | Untested
TC-078 | Dealers | Suspend Dealer | 1. Open active dealer 2. Click Suspend | Status = SUSPENDED; badge turns red; suspended dealers cannot place orders | Functional | Medium | Untested
TC-079 | Dealers | Dealer Monthly Performance Aggregation | 1. Place 3 orders in current month (2 Delivered, 1 Pending) 2. Trigger performance aggregation or GET /dealers/{id}/performance | actualSales = sum of Delivered order values; openOrders = 1 | Integration | Medium | Untested | CRM-049 | Verify tenant isolation
TC-080 | Dealers | Dealer Tier Badge Display | 1. Create dealers with each tier: PLATINUM, GOLD, SILVER, BRONZE 2. Open /dealers list | Each dealer shows correct colored badge: purple/amber/gray/orange | Functional | Low | Untested
SERVICE ANALYTICS
TC-081 | Service Analytics | KPI Dashboard Loads | 1. Navigate to /analytics/service 2. Wait for all 3 API calls to complete | All 6 KPI cards populated; WO aging buckets show bar chart; no errors | Functional | High | Untested
TC-082 | Service Analytics | MTTR Calculation | 1. Complete 2 WOs: one took 2h, one took 4h 2. Check /analytics/service/kpis | mttrHours = 3.0 (average of 2h and 4h) | Functional | High | Untested
TC-083 | Service Analytics | SLA Compliance Rate | 1. Complete 4 WOs: 3 within SLA, 1 breached 2. Check kpis.slaComplianceRatePct | slaComplianceRatePct = 75.0 | Functional | High | Untested
TC-084 | Service Analytics | First Time Fix Rate | 1. Complete 5 WOs: 4 with reopenCount=0, 1 with reopenCount=1 2. Check kpis.firstTimeFixRatePct | firstTimeFixRatePct = 80.0 | Functional | Medium | Untested
TC-085 | Service Analytics | Volume by Type/Priority/Status | 1. Create WOs with different types and priorities 2. Call /analytics/service/volume | byType, byPriority, byStatus maps contain correct counts | Functional | Medium | Untested
TC-086 | Service Analytics | Analytics Cache Invalidation | 1. Load /analytics/service/kpis (cached) 2. Complete a new WO 3. Reload analytics | Cache TTL of 15 min means stale data is acceptable; document expected behaviour | Functional | Low | Untested
INVENTORY ANALYTICS
TC-087 | Inventory Analytics | Dead Stock Report - 90 Day Bucket | 1. Product with last StockTransaction > 90 days ago 2. GET /analytics/service/inventory/dead-stock | Product appears in deadStock90Days list with correct daysSinceLastMovement | Functional | High | Untested
TC-088 | Inventory Analytics | Reorder Recommendations | 1. Product with reorderPoint=20, stockQty=15 2. GET /analytics/service/inventory/reorder | Product appears in reorder list; suggestedReorderQty = reorderQty or reorderPoint*2 | Functional | High | Untested
TC-089 | Inventory Analytics | Top Consumed Parts | 1. Multiple PRODUCTION_OUT transactions for different products 2. GET /analytics/service/inventory/top-consumed?limit=5 | Top 5 products by total consumption returned in descending order | Functional | Medium | Untested
ESCALATION ENGINE
TC-090 | Escalation | Create Escalation Rule | 1. Navigate to /admin/settings/escalation 2. Create rule: SLA_BREACH, conditionMinutes=0, level=L1 3. Save | Rule created; active=true; appears in rules table | Functional | High | Untested
TC-091 | Escalation | SLA Breach Triggers Escalation | 1. Create WO with slaBreached=true 2. Run escalation evaluator 3. Check /escalation/logs | EscalationLog created for the WO; no duplicate log if re-run | Integration | Critical | Untested
TC-092 | Escalation | No Duplicate Escalation Log | 1. WO with slaBreached=true; escalation already fired and unresolved 2. Run evaluator again | No new EscalationLog created; dedup logic prevents duplicate | Edge Case | High | Untested
TC-093 | Escalation | Acknowledge Escalation | 1. Open open escalation in /admin/settings/escalation 2. Click Acknowledge | acknowledgedAt and acknowledgedBy populated; button disabled after | Functional | Medium | Untested
TC-094 | Escalation | Resolve Escalation | 1. Open acknowledged escalation 2. Click Resolve | resolvedAt populated; escalation no longer appears in Open Escalations tab | Functional | Medium | Untested
TC-095 | Escalation | Inactive Rule Not Evaluated | 1. Set escalation rule active=false 2. Create a WO that would trigger the rule 3. Run evaluator | No EscalationLog created for inactive rule | Edge Case | Medium | Untested
HR — ATTENDANCE & LEAVE
TC-096 | Attendance | Check In with Valid GPS | 1. POST /attendance/check-in with valid lat/lng within office geofence | Attendance record created; checkInTime saved; status=PRESENT | Functional | High | Untested
TC-097 | Attendance | Check In Outside Geofence | 1. POST /attendance/check-in with lat/lng far from any office location | Check-in flagged as IRREGULAR or rejected; spoofDetected handled | Security | High | Untested | CRM-017
TC-098 | Attendance | Check Out | 1. Check in at 9:00 AM 2. Check out at 6:00 PM | totalWorkHours = 9.0; status=PRESENT; OT calculated if > shift hours | Functional | High | Untested
TC-099 | Leave | Apply for Leave | 1. Navigate to /leaves 2. Apply for 2-day leave with type=CASUAL 3. Submit | Leave request created with status=PENDING; manager notified | Functional | High | Untested
TC-100 | Leave | Approve Leave | 1. Manager opens leave request 2. Approves | Status = APPROVED; leave balance deducted; employee notified | Functional | High | Untested
RBAC & PERMISSIONS
TC-101 | RBAC | Field Engineer Profile Permissions | 1. Create user with Field Engineer profile 2. Attempt to access /admin 3. Attempt to access /work-orders | /admin returns 403; /work-orders returns 200 with own WOs only | Security | Critical | Untested | CRM-005
TC-102 | RBAC | Service Manager Full Field Service Access | 1. Create user with Service Manager profile 2. Access all field service routes | Assets, Contracts, WOs, Dispatch, Skill Matrix, Analytics all accessible | Security | High | Untested
TC-103 | RBAC | New Tenant Gets Default Profiles | 1. Register new tenant 2. Check profiles collection | 8 system profiles cloned for new tenant; all permission objects present including field service modules | Integration | High | Untested
TC-104 | RBAC | patchMissingPermissions Adds New Modules | 1. Existing tenant with old profiles (no DISPATCH permission) 2. Restart app (runs patchMissingPermissions) 3. Check profile | DISPATCH, SKILL_MATRIX, VENDORS etc. added to all existing profiles | Regression | High | Untested
PROPOSALS & INVOICES
TC-105 | Proposals | Create Proposal | 1. Navigate to /proposals/new 2. Fill line items, GST, discount 3. Submit | Proposal created with version 1; total calculated correctly with GST | Functional | High | Untested
TC-106 | Proposals | Send Proposal to Customer | 1. Open DRAFT proposal 2. Click Send | Status = SENT; sentAt recorded; email notification sent to customer (CRM-007) | Functional | High | Untested | CRM-007 | Email must be wired
TC-107 | Proposals | Accept Proposal | 1. Open SENT proposal 2. Click Accept | Status = ACCEPTED; opportunity stage updated; invoice can be raised | Functional | High | Untested | CRM-007
TC-108 | Proposals | Proposal Versioning | 1. Revise an existing proposal | New version created (v2); old version archived; only latest shown by default | Functional | Medium | Untested
SECURITY & INFRASTRUCTURE
TC-109 | Security | Credentials Not in Source Code | 1. Review application.properties in repo 2. Verify no plaintext credentials | All secrets reference environment variables; no hardcoded passwords or URIs | Security | Critical | Untested | CRM-001 | P0 - fix immediately
TC-110 | Security | SQL/NoSQL Injection Prevention | 1. POST /leads with firstName = '{$where: function(){return true}}' 2. Inspect DB query | Spring Data MongoDB parameterises queries; injection attempt harmless | Security | High | Untested
TC-111 | Security | XSS Prevention in Frontend | 1. Create lead with name = '<script>alert(1)</script>' 2. View lead detail page | Script not executed; React escapes output; name shown as literal text | Security | High | Untested
TC-112 | Security | CORS Policy Enforcement | 1. Send request from disallowed origin (http://evil.com) 2. Check response headers | Request blocked or Access-Control-Allow-Origin header absent/mismatched | Security | High | Untested | CRM-037
TC-113 | Security | Rate Limiting / Brute Force Protection | 1. Send 20 failed login attempts from same IP within 1 minute | After threshold, subsequent attempts return 429 Too Many Requests (if implemented) | Security | Medium | Untested |  | Not yet implemented - log as feature
PERFORMANCE & EDGE CASES
TC-114 | Performance | Large Dataset Pagination | 1. Seed 1000 leads 2. GET /leads?page=0&size=20 | Response in < 500ms; exactly 20 records; totalElements=1000 | Performance | Medium | Untested
TC-115 | Performance | EscalationService findAll() Under Load | 1. Seed 10 tenants × 50 escalation rules each 2. Trigger evaluateAllRules() | All 500 rules evaluated without memory spike; completes in < 30s | Performance | Medium | Untested | CRM-046
TC-116 | Performance | DealerPerformanceService Aggregation at Scale | 1. Seed 5 tenants × 500 orders each 2. Trigger monthly aggregation | Aggregation completes without OOM; per-tenant data correct | Performance | High | Untested | CRM-049
TC-117 | Edge Case | Soft Delete Excludes Records from All Queries | 1. Create and then delete a lead 2. GET /leads; GET /leads/{id} | Deleted lead absent from list; GET by ID returns 404 | Regression | High | Untested
TC-118 | Edge Case | Concurrent WO Closure - Stock Race Condition | 1. Set stock qty=5 for a part 2. Simultaneously close 2 WOs each consuming 5 units | Only one closure succeeds; the other gets 400 Insufficient Stock; final stock ≥ 0 | Edge Case | High | Untested |  | Verify with load test
TC-119 | Edge Case | PO Auto-Reorder Deduplication | 1. Close WO that triggers reorder for Product X 2. Immediately close another WO using Product X | Only one draft reorder PO created for Product X; second run detects existing draft and skips | Edge Case | Medium | Untested | CRM-039
TC-120 | Regression | Sidebar Navigation Permissions | 1. Log in as Field Engineer 2. Inspect sidebar | Only FIELD_SERVICE and HR sections visible; CRM/Admin/Procurement hidden | Regression | High | Untested | CRM-043